Lymphoedema Network Northern Ireland (LNNI)

Annual Report 2012/13

Agreement Cover Sheet

This annual report has been agreed by:

Chair of LNNI Board

Name: 		Mrs Clare McGartland

Date agreed             June 2013

LNNI Project Lead

Name: 		Ms Jane Rankin

Date agreed             June 2013

LNNI Board members agreed the report on

Date agreed            26th June 2013

Annual report review date: AGM, June 2014

- Introduction

This report relates to work undertaken by the Lymphoedema Network Northern Ireland (LNNI) during the year 2012/13.

- Clinical Lead’s address

The Lymphoedema Network Northern Ireland Board has continued to provide an executive platform regarding leadership and direction to the work of the network whilst ensuring that all those with lymphoedema in Northern Ireland have equal access to high quality person centred care.

Whilst the focus of the network is regional, LNNI has extended its links both nationally & internationally.  The LNNI team have been involved in the development of a United Kingdom strategic influencing document and in the regional service proposal for England. The team also submitted a proposal to hold the International Lymphoedema Framework 2014 conference in Belfast and were the runner up host bid. The management team have met twice with senior HSE teams to plan future clinical network development in the South of Ireland with potential for cross-border working. It is rewarding that the key learning’s and success of LNNI have been acknowledged by others and the work replicated in other regions.

The project team would again like to acknowledge the continuous energy and support of the LNNI Board; all members have worked consistently and effectively to develop not only the profile of Lymphoedema, but the service across Northern Ireland. The success of the service and of the network has been recognised nationally which has resulted in recent success in achieving two national awards.

- Background and rationale

In 2002 the Chief Medical Officer commissioned a review of regional lymphoedema services: The Report of the Lymphoedema Services Review Group (2004).

The Lymphoedema Network Northern Ireland (LNNI) was launched on 1st February 2008 with a vision to change the emerging picture of the condition over the next 5 -10 years by initiating:

- Education programmes for at risk patients, referrers and those working with at risk groups/generalists

- An early screening programme/awareness campaign

- Improved referral pathways and local clinic access to specialist teams

- Education programme for specialist staff

- Regional clinic for the most complex patients

This work is supported by the cardiovascular and cancer service frameworks.

Representation on the LNNI Board includes:

- 5 service users

- Clinical leads from each trust

- Commissioner

- General Practitioner

- Assistant Director of commissioning for Regional Services and Strategic Planning, Health and Social Care Board

- LNNI Management team (chair and lead)

The Board also invite a Senior Management Team representative from each trust to encourage communication and understanding. Service managers are also copied into all communications regarding agendas and agreed minutes.

4.0	Meetings schedule and attendance 2011/12

For decision making / approval 60% of key members with a minimum of one patient representative, one trust clinical lead, one stakeholder, and one member from the management team must be present. All meetings achieved the required quorum. In 2012 the Board agreed to reduce meetings to two per year.

|  | 19th June 2012 | 11th December 2012 |
| --- | --- | --- |
| PPI | √ | √ |
| Trust clinical lead | √ | x |
| Trust SMT representative | √ | √ |
| Commissioner | √ | √ |
| LNNI Chair | √ | √ |
| More than 60% Board membership | √ | √ |

5.0 Patient and Carer Feedback Involvement

Regional patient stakeholder events have been held regularly since 2008. In response to previous PPI feedback, the Trust leads from the Western, South Eastern, Southern and Northern Trusts continue to support smaller groups which provide PPI leadership and support for each Trust team.

The Board PPI representatives supported the LNNI long term conditions project addressing the proposal for formal supported self-management classes. This debate has raised the other issues including community Occupational Therapy involvement to support self-care.

The five patient representatives (or alternates), one per Trust, regularly attend LNNI Board  meetings, participate in electronic (e-mail) document reviews/additional communications and  represent LNNI at other events e.g. Long Term Conditions Alliance Northern Ireland meetings. The inclusion of our patient representatives has enriched all aspects of LNNI discussions and ensures that patient voice continues to be at the centre of our work.

- Key Achievements

Throughout the 5th year (Feb 2012 - 13):

- Membership of the British Lymphology Society’s (BLS) Trustee Board, plus obesity, tariff and children’s groups

- Membership of Long Term Conditions Alliance Northern Ireland Board

- 3 Poster presentations and one oral presentation at national BLS 2012 annual Conference including winner of novice presenter prize

- BJN publication (October 2012)

- Cross border relationships developed – Dublin and Donegal meetings and presentations

- Continued to develop the website www.lnni.org : a resource for patients, the public and health care professionals. Emphasis on providing information regarding local access to activity schemes and weight management.

- Continued to lead the regional complex clinic, but have reduced the clinic frequency again from 5 to 6 monthly in recognition of continued up-skilling of service leads

- Third year of regional minimum dataset population for lymphoedema (Lymphdat) Engagement with the Chartered Society of Physiotherapy to publish the “Physio Works” lymphoedema document to influence commissioners and service managers (in partnership with the Association of Chartered Physiotherapists in Oncology and Palliative care and Macmillan)

- Continued support provided to  stakeholders to run local PPI intra-trust groups to influence services (Northern, Southern, South Eastern and Western)

- New reports for the cardiovascular framework created for development and audit beginning 2014Raised the profile of lymphoedema via various regional, national and international conference presentations, including Masters level teaching and bid for the 2014 International Lymphoedema Framework conference.

- Continued to lobby the Department of Health, Political Parties and Ministers regarding key issues affecting the service e.g. increasing levels of obesity, impact of DVTs etc

- Research project: bioimpedence lymphoedema screening programme -  currently recruiting data (sponsored by Friends of Cancer Centre)

- Research project: psychological impact of lymphoedema, assessment of screening tools for clinical use and impact on concordance - new MSc health psychology student leading on project.

- Research project: impact of orthopaedic surgery on patients already treated surgically for breast cancer or those already diagnosed with upper limb lymphoedema.

7.0	Key Challenges for 2012/13

- Incidence change:

The research based estimation of this patient population has changed dramatically since 2008:

- In 2008 -  1.3 per 1000 (2274 patients)

- In 2011 - 2 per 1000 (3600 patients)

- In 2012 - 3.99 per 1000 (potentially 7182 patients).

This change has been corroborated by the LNNI data with 3017 patients held to date and another 400 still to be up loaded (as of 17th June 2013). The initial regional caseload on which the service was designed and financed is therefore considered an underestimation.

- Population change:

Pre 2008 the majority of patients assessed with lymphoedema were related to cancer because existing ad hoc services had been associated with cancer or hospice teams. This inequity has been corrected with equal access for all sufferers, however this new group of patients has proven to be more complex and chronic than those presenting from the cancer-related subgroup. Multiple co-morbidities exist requiring longer treatment periods and more joint working with other teams such as tissue viability.

- Obesity issues:

This new population also has much higher BMI scores than the average population.

- 13.46% of this population has a healthy BMI (i.e. less than 25)

- 59.03% have a BMI greater than 30, which is obese. This is greater than the regional average for the general population (and worsening from 2012 report)

As such the management of this group is made more complex by the health and safety aspects requiring correct handling equipment, additional support staff and domiciliary care.

- New technologies:

Numerous new technologies are entering the lymphoedema market to support established care. The LNNI clinical team must continue to review and, if necessary pilot, new options to increase the efficient use of resources. This may impact on the use of LNNI funding resources.

- Cancer survivorship:

Patients with cancer are living longer due to the developments in cancer management. Patients with cancer-related lymphoedema are therefore living longer and adding to the increasing prevalence rates.

- Future modernisation – the network has continued to utilise data, national/international practice and patient feedback to focus its work plan to continue to increase effectiveness and efficiency.

- Long term conditions model:

The network has reviewed the 2012 DHSSPSNI Long Term Conditions Framework and identified a process to increase the active role of the patient to one of shared partnership with the healthcare staff. This programme, whilst to be developed by specialists, could eventually be managed by band 3s aiming to inform, empower and increase skills to encourage better supported self-care and concordance.

- Supported self-monitoring and discharge:

A scheme has been successfully piloted by the South Eastern HSC Trust team which facilitates patients with well-controlled lymphoedema, and who deem themselves to be competent, to manage their own condition and link with the GPs regarding on-going compression needs. This has reduced the impact of the rising prevalence rates associated with the increasing incidence. Patients will be seen again by the service if they need direct access at any point. The teams are also utilizing the band 3s to do telephone reviews where an acute link needs to be maintained but the presentation is non-complex. It is planned to roll these two improvements out to all trusts. This will impact on band 3 time for administration and assessment, but will reduce the demand on the specialists allowing them to focus on the more complex cases.

- Surgical developments:

Recent improvements in lymphoedema liposuction have made this a viable option for some patients who develop abnormal fat deposits related to the condition. This is not currently available regionally; however some local cases have been referred by the vascular team to Scotland for surgical management. A new vascular plastic surgeon has been employed by the Belfast HSC Trust who is qualified in routine liposuction. He requires some additional training to achieve the lymphoedema techniques. Whilst patients who have this procedure will have a dramatic change in limb shape and quality of life, they will still have to be monitored and have compression garments to maintain the change on a lifelong basis. The vascular team is currently in discussion regarding the potential to develop a regional service which could also receive referrals from the Republic of Ireland for income generation. The surgeon has agreed to attend the LNNI Complex Clinic once a year to review potential candidates whilst funding is debated.

- Developing national linkages:

The network has initiated linkages with the British Lymphology Society and is influencing the work plan of this national group, regarding obesity, tariff and paediatrics in particular. Other links include the national Lymphoedema Support Group, Macmillan, the Charted Society of Physiotherapy and United Kingdom Oncology Nursing Society which provide education opportunities. The network also links with the Welsh and Scottish project leads, sharing outcomes and achievements, and has been integral to the development of the service development project for England.

- Furthering prevention role:

The network currently actively promotes awareness/prevention activities related to cancer surgery. The minimum data set has also highlighted the increasing referral rate as a result of incorrect long term management of DVTs. The team proposes to focus on improving the correct information and treatment pathway (as per 2012 NICE guideline) by working in partnership with clotting clinics and DVT services.

- Developing international linkages:

LNNI has become a stakeholder of the International Lymphoedema Framework which provides access to research and education opportunities. Developing a worldwide minimum data set is a priority.

For further information on the LNNI Board, please follow this link:  www.lnni.org

9.0	Work Plan 2013/14

Appendix A

Appendix A

LNNI Work Plan

June 13 - March 14

Agreement Cover Sheet

This work programme has been agreed by:

Chair of LNNI     Clare McGartland

Date agreed        26th June 2013

LNNI members agreed the report on   26th June 2013

Annual report review date   AGM, June 2014

| Programme headings | Key projects/tasks | Progress |  | Current status | Jun-13 | July -13 | Aug -13 | Sept -13 | Oct -13 |  | Nov -13 | Dec -13 | Jan -14 | Feb -14 | Mar -14 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. Governance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Terms of reference & constitution for board and local trust networks | Last reviewed May 2010. Awaiting regional commissioning changes before next TOR review. |  |  |  | Review TOR etc |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Standards, targets and new policies | Frameworks: New report for cardio vascular framework submitted January 2013. Review March 14 , and draft relevant action plan Obesity Policy (2011). Shared with Dept, ILF and BLS April. Monitor Lymphdat BMI scores. Report at each Board meeting re impact. Liaise/participate with BLS obesity group re national developments |  |  | Board report |  |  |  |  |  |  | Board report |  |  | Report on new CF Framework targets |  |  |  |  |  |  |  |  |
|  | iii. Monitor resources including finance | To be reported at each Board meeting in trust reports – leads. LNNI Lead to keep network budget. Incidence/prevalence figures reviewed annually re impact |  |  | Board report |  |  |  |  |  |  | Board report |  |  |  |  |  |  |  |  |  |  |  |
|  | iv. Incident & complaints monitoring | To be reported at each Board meetings - protocol / line of comms agreed for information to be released from each trust to network - leads. |  |  | Board report |  |  |  |  |  |  | Board report |  |  |  |  |  |  |  |  |  |  |  |
|  | v. Board meetings | Minutes & agendas ratified by board at following meeting & added to website – JR/DS |  |  | Sign off and up load |  |  |  |  |  |  | Sign off and up load |  |  |  |  |  |  |  |  |  |  |  |
| 2. Service development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Report on existing services mapping | Mapping report complete – ratified by Board Dec 09 (Southern, South Eastern, Northern & Belfast HSC Trusts). Western Trust 2011 Project complete |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. Patient database Lymphdat | Population began May 10. 2012 report presented at Stakeholder Event – Feb 2013 Continue to develop reports and letters facilities Report on BMIs at each Board |  |  |  |  |  |  |  |  |  |  |  |  | Demographic/aetiology report 2014 |  |  |  |  |  |  |  |  |
|  | iii. Complex clinics | Clinic protocol, booking system & plan agreed with clinical team. Version 5.0 of policy ratified. Freq reduced further to every 6months in response to learning and patient need. |  |  |  |  |  | Clinic |  |  |  |  |  | Clinic |  |  |  |  |  |  |  |  |  |
|  | iv. Clinical practitioner register | Service mapping tool will inform. Monitor - JR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | v. Education strategy | Framework for strategy ratified by board (AGM June 09) and by public consultation via website. Update work prog for AGM June 13: - Undergrad - specialist - awareness Review new technologies/NICE reviews at each project team meeting |  |  | UU Nursing students Advanced Coban course | Review new ILF practice policy |  |  |  | Study days – NT & WT Awareness trg BLS conf | Possible Foldi trg |  |  | Dermatology lecture |  |  |  |  |  |  |  |  |  |
|  | vi. Long Term Conditions model development | Development of LTCs model for region to build upon expert patient model |  |  | Agree to project at AGM LTCANI meeting Review current local work | Continue links with Scottish Team Review literature |  | Pilot local model in WT |  |  |  |  | Review impact of pilot |  | Potential roll out of project |  |  |  |  |  |  |  |  |
| 3. Communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Website maintenance | Update news, events & circulate newsletter |  |  | Website maintenance fee due | Annual report circulated |  |  |  | Autumn Newsletter circulated |  |  |  |  | Spring newsletter circulated |  |  |  |  |  |  |  |  |
|  | ii. Patient information leaflets | New adjuncts published Mar 11 for use with teams. Purchased additional LSN information All information up to date and available |  |  | Board review funding for re-print |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | iii. Stakeholders and external relationships | 250 Stakeholders registered. Leads to continue to encourage registration. Membership of the International Lymphatic Framework ILF(May 11) DVT regional nurses liaison |  | Joint work with DVT teams re LTC mgt | Dublin HSE meeting | BLS committee meeting |  |  |  | BLS conf |  | BLS committee meeting |  |  | BLS committee meeting |  |  |  |  |  |  |  |  |
|  | iv. Stakeholder events | Continued ST, NT, WT and SET events- leads Regional event with 5 year report – Feb. 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | v. Six month board report | Reduced to annual report as network set up and business on-going - Complete |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | vi. Communication strategy | Framework for strategy ratified (AGM 09)+annual review:. - BJN article - framework submission - obesity policy -Liaison with private health care institutions - UU/QUB liaison - newsletters -intranet articles -BLS committee -LTC Alliance NI -cross border liaison -CSP: Physio Works development (commissioning doc) |  |  | Dublin HSE meeting BMI report Physio Works circulated | BLS committee LTCA meeting |  |  |  | BLS committee /conf | LTCA meeting LNNI newsletter |  |  |  | Framework KPI reports drafted |  |  |  |  |  |  |  |  |
|  | viii. Annual report | Due June 13 AGM (JR) |  |  | Sign off |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | i. Audit programme to monitor practice against agreed standards & targets | 1. Audit based on CREST standards & targets. Remaining 3/46 dependent on QoL research. Lymqol tool instigated 2012 by all trusts 2. Cancer Action Team (national) CAT EBP Pathway audit. Pathway being reviewed by NCAT July 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ii. User satisfaction & focus groups | Patient satisfaction audits initial audit: Dec 11- Feb 12 Continued communication with NILSG/LSNI PPI event – May 2013 |  |  |  |  |  |  |  |  | NILSG/LSNI AGM |  |  | Repeat Pt satisfaction audits |  |  |  |  |  |  |  | New intra trust PPI groups | New intra trust PPI groups |
|  | iii. Monitor action plans | Reports ratified by Board Continuous updates with service managers – include in Board e-mails (with agreed minutes) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Research |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Research i. Clinical practice | Screening of breast cancer pts using bioimpedence. Recruitment completed Dec 2012. New analysis team from UUJ joined team-June 13 |  | On-going data collection | Board report Postersubmission for BLS | SPSS installed. New stats analysis | New project theme drafted |  |  | Poster at BLS conf |  | Data collection complete | Write up | Final report for Friends of CC | Potential new project |  |  |  |  |  |  |  |  |
|  | ii. Epidemiology | Initial demographic and aetiology report using Lymphdat data to highlight local trends. 3rd report at Stakeholder conf (Feb 2013) |  |  |  |  |  |  |  |  |  |  |  |  | Prepare 4th year report |  |  |  |  |  |  |  |  |
|  | iii. Quality of life study | Work ongoing with new UU Health Psychology MSc student under tutorage of Dr Lynn Dunwoody. Will inform QoL tool. |  |  | Agree formats for ethics submission |  | Ethics submission |  |  |  | Data collection |  | Data analysis |  | Report and planned publication |  |  |  |  |  |  |  |  |
|  | iv. Laser lit review | Undergrad sponsorship/mentoring re dissertation COMPLETED |  |  | Published by BLS | Publish by ACPOPC and BLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Not yet started |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Behind schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| On schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Ahead of schedule |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Completed |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | This project plan is signed on behalf of the LNNI Board by: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Chair: |  | Signature: |  |  |  | Date: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Ms Clare McGartland |  | ______________________ |  |  |  | 26th June 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |